FAMILY DAYS COMMISSION

Meeting Minutes

May 11, 2026

A meeting of the Family Days Commission was held on May 11, 2026 at 4:00 p.m. at Village Hall.             Chairwoman Butera called the meeting to order at 4:18 p.m.

Present:

Co-Chair, Angie Butera

Jillian Acuña

Mike Butera

Jon Schallman

Herb Isaacs

Absent:

Phil Bettiker

Caren Ettleman

Also Present:

Justin Keenan, Assistant Village Manager

Mike Brumm, Public Works Analyst

Consideration of Minutes from April 21, 2026 Meeting

Commissioner Acuna made a motion to approve the April 21, 2026 meeting minutes and Commissioner Schallman seconded the motion. The motion passed unanimously.

Public Comment

None

Discussion of Events Timeline

The Commission discussed the overall timeline for the event, confirming that all events are properly represented on the Village website and the Family Days brochure.  Events such as the Rotary Race and the Arts & Crafts fair were discussed due to early start times, coordinating event staff to be on site to ensure these are addressed.

Discussion of Brochure

The Commission reviewed the draft event brochure to confirm this is ready for production.  The Commission discussed filling remaining blank areas in the brochure layout to improve presentation, and to shuffle around the sponsorships for better readability.  The inclusion and placement of event maps on the brochure were also discussed.  The Brochure was approved and will be completed to be sent out to residents by June 5, 2026.

Commissioner Updates

Commissioners provided updates on various event components.  The Fireworks contractor has coordinated with the Fire Department to obtain the fireworks permit, Rides & Games contracts have been finalized, while additional children’s entertainment activities are still being explored.  There were 17 total parade applications submitted online, however there is expected to be near 57 participants for the parade.  Additionally, Village Staff is working in coordination with the Commission to prepare payments for all parade vendors.  Deerfield Public Works is responsible for supplying one float for the parade marshal.  Planning for the Arts & Crafts vendors, Pie Eating Contest, Rotary Race, and sponsorships is ongoing.  The Rotary Race T-Shirt order is in progress, while the Village marketing team is concentrating on pushing online applications for both Pie Eating and Rotary Race.  The Dog Show was discussed and new ribbons have been ordered for the winners.

Other Items for Discussion

The Commission discussed the parade layout and how this differs from last year.  Public parking was discussed, and the limited options available due to the change of parade route and road closures.   Park layout was confirmed.

Top of Form

Next Meeting Date:

June 8, 2026

Adjournment

There being no further business or discussion, Commissioner Schallman moved to adjourn the meeting. Commissioner Acuna seconded the motion. The motion passed unanimously and the meeting was adjourned at 5:07 PM.

Respectfully submitted,
Michael Brumm, Public Works Analyst